## Risk Matrix
RISK MATRIX |  |  | LIKELIHOOD
|  |  | Rare | Unlikely | Possible | Likely | Almost Certain
|  |  | Events that are highly unlikely to happen, possibly occurring less than once in a decade | Events that could occur but are rare, perhaps occurring once every few years | Events that may happen occasionally, such as once or twice a year | Events that are expected to happen frequently, likely several times a year. | Events that are virtually guaranteed to happen, perhaps monthly or even more often.
CONSEQUENCE | Severe | A significant event that could result in catastrophic outcomes, such as complete system failures, loss of critical data, or substantial financial or reputational damage. | HIGH | VERY HIGH | VERY HIGH | EXTREME | EXTREME
| Major | A major event that could cause large losses of data, moderate financial losses, or considerable damage to operations. | HIGH | HIGH | VERY HIGH | VERY HIGH | EXTREME
| Moderate | An event that causes noticeable disruptions but can be managed or contained without severe long-term effects. | LOW | MEDIUM | MEDIUM | HIGH | VERY HIGH
| Minor | An event with minimal impact, causing some inconvenience but not disrupting major operations | VERY LOW | LOW | MEDIUM | MEDIUM | HIGH
| Insignificant | A very low-impact event that would likely go unnoticed or cause trivial inconvenience. | VERY LOW | VERY LOW | LOW | MEDIUM | MEDIUM

## Risk Assessment
Context - Asset(s) that we are trying to protect
Sensitive Information: Customer data, intellectual property, or trade secrets. Financial Information: Transaction records, accounting data, or audit trails. Physical Assets: Hardware, equipment, or facilities. Operational Continuity: Systems and processes that ensure service delivery.
Risk |  |  |  |  | Inherent Risk Rating |  |  | Current Risk Rating |  |  |  |  | Target Risk Rating
ID | Title | Description | Sources or Causes of Risk | Consequences of Risk | Likelihood | Consequence | Risk Level | Existing control measures | Effectiveness of exisitng control measures | Likelihood | Consequence | Risk Level | Additional control measures | Effectiveness of additional control measures | Likelihood | Consequence | Risk Level
R01 | Data Breach | Unauthorized access to or theft of sensitive data caused by cyberattacks, insider threats, or inadequate security measures. | Phishing attack, malware infection, lack of employee awareness, or unpatched software vulnerabilities. | Loss of sensitive customer data, financial penalties due to regulatory non-compliance (e.g., GDPR fines), and reputational damage. | Likely | Severe | EXTREME | Firewalls, encryption, multi-factor authentication, employee training. | Good Existing measures like firewalls, encryption, and MFA are solid defenses. Employee training also adds value but can vary in quality. However, they are not infallible, especially against sophisticated attacks or human error. | Possible | Major | VERY HIGH | Treat Enhanced employee training, AI-driven threat detection, penetration testing, stricter access controls. | Excellent These measures are highly effective in preventing data breaches. Enhanced training and AI-driven detection systems significantly reduce the likelihood of a breach, while stricter access controls and regular testing ensure that vulnerabilities are minimized. The combination of technical and human-centered measures creates a robust defense against breaches. | Unlikely | Major | HIGH
R02 | System Downtime | Unplanned outages or system failures that prevent normal business operations, resulting from technical issues, power failures, or inadequate infrastructure. | Power outages, server failures, or insufficient system redudancy. | Loss of revenue, inability to service customers, reduced customer trust, and operational delays. | Possible | Major | VERY HIGH | Backup power supplies, system monitoring, and redundant infrastructure. | Moderate While existing measures such as backup power and redundancy provide some protection, they might not address all potential causes of downtime (e.g., software failures or cyberattacks). The controls reduce risk but may leave gaps in rapid recovery. | Unlikely | Moderate | MEDIUM | Treat real-time system monitoring, cloud backups, disaster recovery plans, redundant infrastructure. | Good These measures are effective at reducing downtime. Real-time monitoring and failover systems help identify and resolve issues quickly, while cloud backups and disaster recovery plans ensure minimal impact during downtimes. However, complete elimination of downtime is unlikely, so the rating is "Good" rather than "Excellent." | Rare | Moderate | LOW
R03 | Insider Threat | Security risks posed by individuals within the organization, whether through malicious intent or accidental actions that compromise critical assets. | Malicious intent by a disgruntled employee, accidental misuse of priveleged access, or weak access controls. | Unauthorized access to confidential data, sabotage of critical systems, or exposure of intellectual property. | Possible | Severe | VERY HIGH | Access controls, employee monitoring, and whistleblower policies. | Moderate Basic access controls and monitoring help reduce the risk of insider threats, but they may not be sufficient to address all potential scenarios (e.g., intentional sabotage or social engineering). Whistleblower policies provide some mitigation but are reactive rather than proactive. | Unlikely | Severe | VERY HIGH | Treat Behavioral monitoring, enhanced background checks, RBAC, security awareness programs. | Good These controls significantly mitigate the risk of insider threats. Behavioral monitoring and RBAC (Role-Based Access Control) help detect and prevent malicious or negligent actions. Background checks and security programs reduce the likelihood of such incidents. However, human behavior is difficult to fully predict, so while the measures are strong, they cannot guarantee prevention, leading to a "Good" rating. | Rare | Major | HIGH
R04 | Natural Disaster | Severe natural events, such as floods or earthquakes, that physically damage assets, disrupt operations, and require extensive recovery efforts. | Floods, earthquakes, hurricanes, or fires impacting office locations or data centers. | Destruction of physical assets, disruption of operations, and extended recovery periods due to a lack of disaster recovery plans. | Rare | Severe | HIGH | Disaster recovery plans, insurance, and physical safeguards (e.g., fire suppression systems). | Moderate Current disaster recovery plans and insurance reduce financial and operational impact. Physical safeguards (e.g., fire suppression) help protect assets, but these measures do not prevent disasters from occurring. The overall control is limited by the unpredictability and severity of such events. | Rare | Moderate | LOW | Transfer / Treat Business continuity planning, geographically distributed backups, physical safeguards, insurance. | Moderate While these measures are effective at reducing the impact of a natural disaster, the inherent unpredictability and potential severity of natural disasters mean that the controls cannot fully mitigate the risk. Business continuity planning and insurance provide significant recovery mechanisms, but the effectiveness of the measures is somewhat limited by the nature of the event itself. | Rare | Moderate | LOW
R05 | Supply Chain Disruption | Interruptions in the supply chain due to vendor issues, geopolitical events, or logistics delays, leading to operational bottlenecks and financial losses. | Vendor bankruptcy, geopolitical instability, or delays due to transportation/logistics failures. | Increased costs, inability to meet customer demand, and loss of competitive advantage. | Likely | Major | VERY HIGH | Diversified suppliers, inventory stockpiling, and supply chain monitoring tools. | Good Diversifying suppliers and maintaining stockpiles are effective at mitigating the risk of supply chain disruptions. Monitoring tools provide early warnings, but external factors (e.g., geopolitical issues or natural disasters) may still disrupt the supply chain. | Possible | Moderate | MEDIUM | Treat / Transfer Supplier diversification, buffer stock, supply chain monitoring tools, contingency agreements. | Good These measures are effective at reducing the likelihood and impact of supply chain disruptions. Supplier diversification and contingency agreements ensure that alternatives are available in case of disruptions. Buffer stock provides a buffer to weather delays. Monitoring tools help predict potential disruptions. However, disruptions are sometimes inevitable, and external factors may still cause interruptions despite these controls, so "Good" is a suitable rating. | Unlikely | Moderate | MEDIUM
Note on L6: Excellent Control - Highly effective and very fit for purpose. It substantially reduces the likelihood and/or consequence of the risk. It is cost effective. Good Control - Effective and fit for purpose. It reduces the likelihood and/or Consequence of the risk. It is relatively cost effective. Moderate Control - Moderately effective in reducing likelihood and/or consequence. May be able to be improved. May not be entirely cost effective. Weak Control - Does not exist, or is inadequate, ineffective or marginally effective in reducing likelihood and/or consequence. It is not cost effective
Note on R6: Excellent Control - Highly effective and very fit for purpose. It substantially reduces the likelihood and/or consequence of the risk. It is cost effective. Good Control - Effective and fit for purpose. It reduces the likelihood and/or Consequence of the risk. It is relatively cost effective. Moderate Control - Moderately effective in reducing likelihood and/or consequence. May be able to be improved. May not be entirely cost effective. Weak Control - Does not exist, or is inadequate, ineffective or marginally effective in reducing likelihood and/or consequence. It is not cost effective